## Sheet1 (hidden)
Assigned | Critical
In Progress | High
Escalated | Medium
Pending Close | Low
Closed

## Sheet6 (hidden)
Status-Risk | Probability | Impacts
Opened | 5 | 4
Closed-Diverted | 4 | 3
Closed | 3 | 2
Pending Closed | 2 | 1
Realized | 1

## Getting Started
Getting Started with the Master Project Log
The purpose of this documentation is to provide users of this master log with contextual information, definitions, and / or supporting details regarding the usage of this log. Each worksheet tab columns are defined and described below.
Change Request Log
CR-ID | The number that uniquely identifies the item in the log for the worksheet. Typically a number, applied sequentially as the items are logged.
Project | The name of the project the change request is primarily related to and will be modifying.
CR Name | The short name of the change request, a simple label or sentence that the team may use in referencing the need.
Description | Detailed description of the change request, including any supporting context, history, or other information that provides stakeholders with understanding of the change needed.
Status | A single designation of change request status including: - Submitted: The change request has been submitted to be reviewed. - Approved: The change request has been approved by required parties. - In Progress: The change is in progress of being completed. - Pending Close: The change request has been completed and is being communicated. - Closed: The change request has been completed and all stakeholders have been notified.
Origination Date | The date the change request was first identified or originated as a concern for the project.
Closed Date | The date the change request was closed.
Priority | The relative priority assigned to the change request; the options are: - Critical: The need generating the CR is impacting scope, schedule, or budget. - High: The need generating the CR has a high probability of immediate impact on scope, schedule, or budget. - Medium: The need generating the CR has a medium probability of immediate impact on scope, schedule, or budget. - Low: The need generating the CR has a low probability of immediate impact on scope, schedule, or budget.
Triple Constraint Impact | Impact of the Change Request on either Scope, Time, and/or Cost
Follow Up Action Needed | Additional actions that need to be taken after completion of the change request.
Responsible Party | Individual responsible for completing follow up items.
Updates | Any updates during the life of the change request that need to be tracked.
Action Items / Closed-Action Items Worksheets
ID | The number that uniquely identifies the item in the log for the worksheet. Typically a number, applied sequentially as the items are logged.
Source | The event, occurrence, or person that generated the action item.
Action Item | The short name of the action, a simple label or sentence that the team may use in referencing the need.
Status | A single designation of action status; the options are: - Assigned: The proper owner / worker of the action has been identified. - In Progress: The action is being worked according to the resolution plan. - Escalated: Expected progress has not been made and the need has been escalated. - Pending Close: The action has been completed and is being communicated. - Closed: The action has been completed and all stakeholders have been notified.
Item Owner | The team member that owns the action item, has the responsibility for taking or assuring action.
Description | Detailed description of the action item, including any supporting context, history, or other information that provides stakeholders with understanding of the action needed.
Target Date | The current target date for action established by the project priorities or the owner of the action.
Completion Date | The date the action was completed.
Target Date | The original target date established for the action for reference purposes should the target date change over the course of execution.
Updates | Logged textural updates regarding progress for the action; date / time stamp of the update is provided should multiple reporting periods be spanned.
Assumption List Worksheets
Assumption ID | The number that uniquely identifies the item in the log for the worksheet. Typically a number, applied sequentially as the items are logged.
Category | The category of the assumption. These should be defined for each project.
Assumption | Description of the assumption made.
ID'd Date | Date the assumption was identified.
ID'd By | Individual who identified the assumption.
Confidence | Select one of the below values to represent the confidence level: - 1: Nearly a fact - 2: Probably true - 3: More than likely not true - 4: Guess (uncertain)
Severity | The impact of the assumption if its wrong. Select one of the below values to represent severity: - 1: Little to no impact - 2: Marginal - 3: Significant (may require contract revision) - 4: Catastrophic (failure likely)
Assumption Score | The confidence and severity level impact the overall score. Higher score assumptions require a greater amount of attention.
Assumption Owner | The person responsible for validating the assumption.
Due Date | The date by which the responsible person should resolve the assumption.
Updates | Updates about the assumption as new information becomes available. This could include changes in the assumption, updates in the confidence level, or new information about the basis of the assumption.
Issues / Closed-Issues Worksheets
ID | The number that uniquely identifies the item in the log for the worksheet. Typically a number, applied sequentially as the items are logged.
Project | The name of the project the issue is primarily related to, either impacting or causing impact.
Name | The short name of the issue, a simple label or sentence that the team may use in referencing the issue.
Status | A single designation of issue status; the options are: - Assigned: The proper owner / worker of the issue has been identified. - In Progress: The issue is being worked according to the resolution plan. - Escalated: Expected progress has not been made and the issue has been escalated. - Pending Close: The issue resolution has been attained and is being communicated. - Closed: The issue has been resolved and all stakeholders have been notified.
Action Required By | For the issue to be identified, clarified, or otherwise resolved, action is required by the person or people specified here. Names should be listed.
Assigned To | The individual that is accountable for resolving or assuring resolution of the issue according to an agreed upon plan and within the target date. This should be a single person.
Origination Date | The date the issue was first identified or originated as a concern for the project.
Closed Date | The date the issue reached Closed Status.
Priority | The relative priority assigned to the issue; the options are: - Critical: Issue is impacting scope, schedule, or budget. - High: Issue has a high probability of immediate impact on scope, schedule, or budget. - Medium: Issue has a medium probability of immediate impact on scope, schedule, or budget. - Low: Issue has a low probability of immediate impact on scope, schedule, or budget.
Description | Detailed description of the issue, including any supporting context, history, or other information that provides stakeholders with understanding of the issue.
Triple Constraint Impact | Impact of the Change Request on either Scope, Time, and/or Cost
Target Date | The current target date for issue resolution established by the project priorities or the owner (assigned to) of the issue.
Baseline Date | The original target date established for the issue resolution for reference purposes should the target date change over the course of execution.
Updates | Logged textural updates regarding progress for the issue resolution plan; date / time stamp of the update is provided should multiple reporting periods be spanned.
Risks / Closed-Risks Worksheets
Risk ID | The number that uniquely identifies the item in the log for the worksheet. Typically a number, applied sequentially as the items are logged.
Project | The name of the project the risk is primarily related to, either impacting or causing impact.
Description | Detailed description of the risk, including any supporting context, history, or other information that provides stakeholders with understanding of the risk.
Status | A single designation of risk status; the options are: - Open: The risk item has been defined and captured. - Closed-Diverted: Risk mitigation plans have succeeded. - Closed: The risk has been resolved and all stakeholders have been notified. - Pending Close: The risk resolution has been attained and is being communicated. - Realized: The risk event has occurred invoking contingency plans.
Assessment | The numerical product of Probability, Project Impact, and Business Impact; provides a quantification of the risk for prioritization and ranking purposes.
Probability | An indication of risk event probability; the options are: - 5 - Very Likely to Occur - 4 - Likely to Occur - 3 - May Occur - 2 - Unlikely to Occur - 1 - Very Chance of Low Occurrence
Project Impact | An indication of impact to the effort from the project's perspective; the options are: - 4 - Critical Path Impact (Showstopper, will impact End Date) - 3 - High Impact (may impact End Date, will impact KTMs) - 2 - Medium Impact (may impact KTMs within schedule, but not the End Date) - 1 - No Impact
Business Impact | An indication of impact to the effort from the business's perspective; the options are: - 4 - Customer Impact (cannot receive service/project) - 3 - Operational Impact, but no Customer Impact - 2 - Operational Inconvenience, but no Operational or Customer Impact - 1 - No impact
Triggers | Specification of what will trigger the risk event for the effort. Can be one or many things.
Phase | The specified phase of the project during which the risk event is forecast to occur.
Response | The planned response to the risk (Avoid, Mitigate, Transfer, or Accept.)
Response Plan | The specific course(s) of action that will be taken to avoid, mitigate, or transfer the risk. If the planned response is "accept," list the person(s) who approved this response.
Contingency Plan | If needed, list the steps to be taken if the planned response cannot be carried out or proves ineffective at managing the risk.
Updates | Logged textural updates regarding progress toward managing the risk; date / time stamp of the update is provided should multiple reporting periods be spanned.
Owner | The team member that owns the risk item, has the responsibility for assuring mitigation plans as well as formulating the contingency plan.

## Change Requests
Change Requests for <Project>
CR-ID | CR Name | Description | Status | Origination Date | Closed Date | Priority | Triple Constraint Impact (Scope, Time and/or Cost) | Follow up Action Needed | Responsible Party | Updates

## Action Items
Action Items for <Project>
ID | Source | Action Item | Status | Item Owner | Description | Target Date | Completion Date | Baseline Date | Updates

## Assumptions
Assumption List For <Project>
Assumption ID | Category | Assumption | ID'd Date | ID'd By | Confidence | Severity If Wrong | Assumptions Score (Confidence x Severity) | Assumption Owner | Due Date | Updates
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0

## Data Validation (hidden)
Assumption Confidence/Severity
1
2
3
4

## Issues
Issues Log for <Project>
ID | Name | Status | Status Date | Action Required By | Assigned To | Origination Date | Closed Date | Priority | Description | Triple Constraint Impact (Scope, Time and/or Cost) | Target Date | Baseline Date | Updates

## Risks
Risks Register for <Project>
Risk ID | Description | Status | Assessment | Probability | Project Impact | Business Impact | Triggers | Phase | Response (Avoid, Mitigate, Transfer, or Accept) | Response Plan | Contingency Plan | Updates | Owner
0
0
0
0
0
0
0
0
0
0

## Key Decisions
Key Decisions for <Project Name>
ID | Project | Decision Needed | Status | Item Owner | Decision Stakeholders | Origination Date | Decision Outcome | Target Date | Completion Date | Critical Date | Orig. Target Date | Updates